## Logistics and Operations
Task | Person Responsible | Progress? | Comments
Event Coordination and Logistics
Decide on date | E-Board | TRUE | Do early! You should schedule this as a talking point in December. Spaces on campus fill up QUICK. Consider events that happen yearly (undergrad expo, world health day symposium, jazz fest, college-specific expos - IDEAS, Engineering) | 2026-03-13
Coordinate picking up Easels | Rafiatu | TRUE
Pick up Easels | KT | FALSE | Where?
Return Easels |  | FALSE
Order Catering | Rafiatu | TRUE | Order numbers:
Confirm Catering Details | Rafiatu | TRUE
Reserve Space | Rafiatu | TRUE | International Ballroom
Confirm Space Layout Details | Rafiatu | TRUE
Decorations? [For 25-26 GPSA E-Board to consider] | KT,ZAC, Rafiatu | FALSE | Decorations: UI ballons, GPSA swag
Hire a photographer [Marketing] |  | FALSE
Marketing
GPSA Expo Flyer Creation | KT | TRUE
GPSA Expo Flyer Distribution |  | TRUE | Use university list of flyer bulleting board locations
GPSA Expo reminder e-mails (1/week until abstract submission deadline; 1 general reminder the week before) | KT | TRUE
Daily Register | KT | TRUE | Allow 2-3 days for posting. You can detail how often you want it to be published.
MyUI | KT | FALSE | Submit the Wed before you want it to go out. Use for abstract submission and general event invitation
ISUB screens | KT | FALSE | Use submission form. Allow 7 business days for it to be posted. Can only be posted for 14 days - use strategically.
IRIC screens | KT | TRUE | Coordinate with Russell (). Allow 2-3 business days for it to be posted.
COGS e-mail | KT | FALSE | Coordinate with COGS office to send out ~ 1-2 weeks before the event
Create University Calendar Event | KT | TRUE
Student Participant Management
Create Submission Portal for Abstract | Rafiatu | TRUE | Coordinate with COGS
Create verbiage for abstract submission inquiry |  | TRUE | Build upon previous materials
Create verbiage for abstract acceptance e-mail | Rafiatu | TRUE | Make sure to include Expo schedule and logistics so students can plan ahead
Create verbiage for abstract rejection e-mail |  | TRUE | Build upon previous materials
Create expo pamphlet? | KT | TRUE
FALSE
Guest Judges Management
Call for Judges - email | Phillip | TRUE | Should go out by mid-february. Ask President for support because they attend Faculty meeting and have regular meetings with faculty on campus.
Thank you cards/gift | KT & Rafiatu | FALSE | See what small thing we could get from the vandal store
FALSE
FALSE
FALSE
FALSE
FALSE
Special Guest Management
Invitation to campus partners e-mail |  | FALSE
Gradsexpo@13-catering login password
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Send e-mail to ensure order has been received and accepted
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider using Qualtrics instead of Slate. Whatever you do ensure you get access to the software/survey AS SOON as it is created
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For 25-26 GPSA eboard to consider. Could also be a virtual pamphlet if you don’t want to waste money and time printing.

## Judges
Name | Department | Emails | Accepted? |  | Final List | NAME | DEPARTMENT | CONTACT | Judging Assignments
Scott Green | President | scottgreen@uidaho.edu | FALSE | Declined |  | Barrie Robison | Director, IIDS, IMCI - COS | brobison@uidaho.edu
Leslie Edgar | Dean-CALS | ledgar@uidaho.edu | FALSE | Declined |  | Beth Ropski | CETL - EHHS | eropski@uidaho.edu
Herbert Hess | Dept Chair, Elec & Comp Engr | hhess@uidaho.edu | TRUE |  |  | Jennifer Wilcox | Former GPSA/Biology | jwilcox@uidaho.edu
Michael Decker | Director, GSS - COGS | mdecker@uidaho.edu | FALSE | Declined |  | Aaron Johnson | Assoc Chair, CAA | acjohnson@uidaho.edu
Kristin Haltinner | CLASS | khaltinner@uidaho.edu | FALSE |  |  | Michael Brandt | Faculty, Theatre Arts | brandt@uidaho.edu
Shelly K. Mc Guirre | Director FCS, CALS | smcguire@uidaho.edu | FALSE |  |  | Ann Frost | Assoc Dean Grad Studies, EHHS | afrost@uidaho.edu
Barrie Robison | Director, IIDS, IMCI - COS | brobison@uidaho.edu | TRUE |  |  | Margaret Pinnell | Director, CETL | mpinnell@uidaho.edu
Tracey Peters | Ani, Vet, Food Sci (COS?) | tpeters@uidaho.edu | TRUE |  |  | Brian Tibayan | Post Doc Fellow, EHHS | btibayan@uidaho.edu
Beth Ropski | CETL - EHHS | eropski@uidaho.edu | TRUE |  |  | Ginny Lane | FCS, Nutritional Sci | vlane@uidaho.edu
Erin Chapman | FCS - CALS | chapman@uidaho.edu | FALSE | Declined |  | Ginger Carney | Dean, COS
Chris Marx | COS Biological Sci | cmarx@uidaho.edu | FALSE |  |  | Herbert Hess | Dept Chair, Elec & Comp Engr | hhess@uidaho.edu
Holly Wichman | IMCI/ COS | hwichman@uidaho.edu | FALSE |  |  | Rowdy Sanford | Engineering (Elec & Comp)
Alyssa Kreikemeier | HIST - CLASS | akreikemeier@uidaho.edu | FALSE |  |  | Tracey Peters | Ani, Vet, Food Sci (COS?) | tpeters@uidaho.edu
Rula Awwad-Rafferty | Art & Arch | rulaa@uidaho.edu | FALSE |  |  | Phillip Hagen | GPSA
Phillip Hagen | GPSA |  | TRUE |  |  | Ritchie Thaxton | GPSA
Ritchie Thaxton | GPSA |  | TRUE |  |  | RITA Franco | GPSA
RITA Franco | GPSA |  | TRUE |  |  | KT Turner | GPSA
KT Turner | GPSA |  | TRUE |  |  | Zachary Foley | GPSA
Zachary Foley | GPSA |  | TRUE |  |  | Rafiatu Salia | GPSA
Ting-Yen Shih | Elec & Comp Engr |  | FALSE
Suzie Long | Dean, Engineering |  | FALSE
Marc Jean | Elec & Comp Engr |  | FALSE
Stefan Toheanu | COS Math |  | FALSE
James Bull | COS Biological Sci |  | FALSE
Rowdy Sanford | Engineering (Elec & Comp) |  | TRUE
Eric Wolbrecht | Chair, Mech Engineering |  | FALSE
Jennifer Wilcox | Former GPSA/Biology |  | TRUE
Torrey Lawrence | Provost |  | FALSE | DEclined
Chris Nomura | VP Research & Econ Dev |  | FALSE | Declined
Jerry McMurtry | Dean, COGS |  | FALSE
Aaron Johnson | Assoc Chair, CAA | acjohnson@uidaho.edu | TRUE
Blaine Eckles | Dean of Students |  | FALSE | Declined
Brian Kennedy | CNR - Fish & Wildlife | kennedy@uidaho.edu | FALSE
David Ausband | CNR, ID Coop Fish & Wildlife Research | dausband@uidaho.edu | FALSE

## 2026 Student Presenter List
Date submitted | Vandal Number (include "V")* | First Name* | Last Name* | VandalMail* | Authors* | Select your Current Program and Degree* | Upload a copy of your abstract here* - Name | Type of work | Accepted? | Project Number
2026-01-27 15:33 | V00818837 | Sameer | Mankotia | mank8837@vandals.uidaho.edu | Sameer Mankotia, Daniel Conte De Leon , Jennifer Johnson-Leung | Computer Science-PHD | Abstract_SameerMankotia.pdf | P | TRUE
2026-01-27 15:52 | V00998289 | Nate | Nadal | nnadal@uidaho.edu | Nate Nadal | Natural Resources - Fish and Wildlife Science and Management Option-MNR | Abstract NN.docx | P | TRUE
2026-01-28 00:59 | V00998894 | Andrea | Schmutz | schm8894@vandals.uidaho.edu | Andrea Soleta Schmutz, Juhee Kim | Education-PHD | GPSA Abstract.docx | P | TRUE
2026-02-01 16:27 | v00988631 | Sahithi | Thota | thot8631@vandals.uidaho.edu | Sahithi Thota | Electrical Engineering-PHD | abstract for GS Uidaho.docx | P | TRUE
2026-02-03 15:31 | V00709993 | Japneet | Kukal | kuka9993@vandals.uidaho.edu | Japneet Kukal, Lorena A. Portilla, Brian Via, Lucila M. Carias, Maria Auad, Manish Sakhakarmy, Sushil Adhikari, Armando G. McDonald | Natural Resources-PHD | Abstract.docx | P | TRUE
2026-02-04 10:52 | V00913672 | Ruth | Azike | azik3672@vandals.uidaho.edu | Azike Ruth Chinazor, Armando McDonald, Ezra BAR-ZIV | Environmental Science-MS | GPSA SYMPOSIUM ABSTRACT.pdf | P | TRUE
2026-02-09 14:35 | V00655902 | Sodiq | Yusuf | yusu5902@vandals.uidaho.edu | Sodiq Yusuf, Michael Maughan and Armando McDonald | Natural Resources-PHD | Abstract FPS_Sodiq.docx | P | TRUE
2026-02-10 14:33 | V00010434 | Marilyn | Stein | stei0434@vandals.uidaho.edu | Marilyn Stein, Yimin Chen, Ann Frost | Nutritional Sciences-PHD | MarilynSteinAbstract.docx | P | TRUE
2026-02-10 17:32 | V00900766 | Edison | Reyes Proano | reye0766@vandals.uidaho.edu | Edison Reyes-Proano, Gardenia E. Orellana, Jeffrey Chojnacky, Apekshya Senchuri, Erik J.Wenninger, and Alexander V. Karasev. | Plant Science-PHD | GPSA_Abstract_FINAL.pdf | P | TRUE
2026-02-11 12:13 | V00969291 | Emmanuella | Afolabi | afol9291"vandals.uidaho.edu | Emmanuella Afolabi | Anthropology-MA | Abstract.docx | P | TRUE
2026-02-11 17:33 | V00973546 | Luna | Migueles Miralles | Migu3546@vandals.uidaho.edu | Luna Migueles Miralles | Art-MFA | Luna_Spring 2026 GPSA Research Symposium.pdf | AW | TRUE
2026-02-12 10:02 | V00974371 | Keeya | Beausoleil | beau4371@vandals.uidaho.edu | Keeya Beausoleil, Timothy Bartholomaus, Alison Criscitiello, Eric Mittelstaedt, Elowyn Yager | Geology-MS | GPSA_Abstracts_Beausoleil.pdf | P | TRUE
2026-02-12 14:23 | V00889148 | Ashton | Sellke | sell9149@vandals.uidaho.edu | Ashton Sellke, Timothy Prather | Plant Science-MS | GPSA_Abstract_Sellke.pdf | P | TRUE
2026-02-12 16:09 | V00738150 | Yuan | Yuan | yuan8150@vandals.uidaho.edu | Yuan Yuan | Biological Engineering-PHD | Comparative Evaluation of Continuous-Flow Liquid-Phase Plasma Discharge as a Non-Thermal Alternative to Conventional Milk Pasteurization.pdf | P | TRUE
2026-02-13 03:37 | V00928493 | Shahriar Md Arifur | Rahman | rahm8493@vandals.uidaho.edu | Shahriar Md Arifur Rahman, Chris A.B. Zajchowski, Muhammad Moniruzzaman, Joohee Lee, & Hana Kim | Environmental Science-PHD | Rahman et al. 2025_Abstract.docx | P | TRUE
2026-02-13 04:40 | V01006711 | Jacob | Spickelmire | spic6711@vandals.uidaho.edu | Jacob Spickelmire | English-MA | Research Project Abstract - Spring 2026 GPSA Research Symposium - Spickelmire.pdf | P | TRUE
2026-02-13 08:19 | V00790733 | Ariana | Cerreta | cerr0733@vandals.uidaho.edu | Ariana L. Cerreta and David E. Ausband | Natural Resources-PHD | GPSA-Research-Symposium-Abstract_Cerreta_Ariana.docx | P | TRUE
2026-02-13 11:10 | V00765899 | Hannah | Stolfus | stol5899@vandals.uidaho.edu | Hannah Stolfus | Agricultural Education-MS | GPSA Expo Abstract_Stolfus.pdf | P | TRUE
2026-02-13 12:15 | V00767704 | Paige | O'Callaghan | ocal7704@vandals.uidaho.edu | Paige O'Callaghan | Theatre Arts-MFA | GPSA Research Symposium Abstract - O'Callaghan.pdf | AW | TRUE
2026-02-13 12:55 | V00661754 | Timothy | Stevens | stev1754@vandals.uidaho.edu | Daniel Robertson, Timothy Stevens` | Mechanical Engineering-PHD | Abstract for Grad Symposium.docx | P | TRUE
2026-02-13 14:46 | V00975899 | Kyle | Silligman | sill5899@vandals.uidaho.edu | Kyle Silligman | Art-MFA | GPSA Annual Graduate Expo - Abstract.pdf | AW | TRUE
2026-02-13 16:15 | V01051482 | Evelyn | Roldan Vernon | rold1482@vandals.uidaho.edu | Evelyn Roldán Vernon, Wilton Pérez, and Ginny Lane | Nutritional Sciences-PHD | GPSAabstractEroldanVernon.docx | P | TRUE
2026-02-13 17:08 | V00781344 | Isaac | Looney | loon1344@vandals.uidaho.edu | Isaac Looney, Daniel Robertson | Mechanical Engineering-MS | DARLING Abstract.pdf | P | TRUE
2026-02-13 17:28 | V00880118 | Hussain | Qazaq | qaza0118@vandals.uidaho.edu | Ginny Lane and Hussain Qazaq | Nutritional Sciences-PHD | Blaine County Cost of Living and Food Security Survey March.docx | P | TRUE
2026-02-13 19:22 | V00815393 | Leela | Appili | appi5393@vandals.uidaho.edu | Leela Appili | Plant Science-PHD | Abstract 2026.docx | P | TRUE
2026-02-13 22:33 | V01112418 | Alireza | Majidi | maji2418@vandals.uidaho.edu | Alireza Majidi, Edris Afsharkohan, Mahdi Hejazi, Mojtaba Shafiee | Nutritional Sciences-MS | Abstract of FI - MS%2C GPSA Alireza Majidi.pdf | P | TRUE
2026-02-13 23:33 | V00666244 | Benjamin | Morenas | more6244@vandals.uidaho.edu | Benjamin Morenas, Ekow Agyekum-Oduro, Alia Nasir, Yuan Yuan, Sarah Wu | Biological Engineering-MS | Title_Abstract_BenjaminMorenas.pdf | P | TRUE
2026-02-14 00:38 | V00939219 | Ahmad | Mukhtar | mukh9219@vandals.uidaho.edu | Ahmad Mukhtar, Yuan Yuan, Jonathan Stromberg, Ben Morenas, Sarah Wu | Chemical Engineering-PHD | Abstract_2026.docx | P | TRUE
2026-02-14 02:13 | V00853445 | Ekow | Agyekum-Oduro | agye3445@vandals.uidaho.edu | Ekow Agyekum-Oduro, Ahmad Mukhtar, Sidra Saqib, Robinson Ndeddy Aka, Sarah Wu | Chemical Engineering-PHD | Abstract.docx | P | TRUE
2026-02-14 03:08 | V00769466 | Alia | Nasir | nasi9466@vandals.uidaho.edu | Alia Nasir, Benjamin Morenas, Dinithi Mohotti, Ekow Agyekum-Oduro, Sarah Wu | Biological Engineering-PHD | Abstract_GPSA EXPO MARch 2026 .docx | P | TRUE
FALSE
DECLINED
2026-02-05 12:49 | V00779494 | Brandon | Light | blight@uidaho.edu | Brandon N. Light, Andrew T. Hudak, Mark Kimsey, Andrew Larson, Charles Goebel | Environmental Science-PHD | GPSA2026_abstract_lidar_FINAL.docx | P | FALSE | Declined
2026-02-12 10:54 | V01039119 | Sofia | Blair | blai9119@vandals.uidaho.edu | Sofia Blair, Timothy Prather | Plant Science-MS | Abstract.docx | P | FALSE | Declined
2026-02-12 20:54 | V01012094 | MD SAYED | HASAN | hasa2094@vandals.uidaho.edu | M.S. Hasan, M. Chahine, J.B. Hall, G.E. Chibisa | Animal Science-MS | Abstract_Md Sayed Hasan_.pdf | P | FALSE | Declined
2026-02-13 23:05 | V00891693 | Amal | Thelakkadan | thel1693@vandals.uidaho.edu | Amal Thelakkadan, Ginny Lane, Colin Xu, Qingyu Jiang, Mojtaba Shafiee | Nutritional Sciences-MS | Amal Thelakkadan - Abstract GPSA.docx | P | FALSE | Declined

## Invitees
Name | Department | Emails
Shauna Corry | Dean, CAA | sent - judge |  | FALSE | Michael Brandt | Faculty, Theatre Arts
Lisa Victoravich | Dean, Bus & Econ | sent - judge |  | FALSE | Ann Frost | Assoc Dean Grad Studies, EHHS
Blooke Blevins | Dean, EHHS | sent - judge |  | FALSE | Margaret Pinnell | Director, CETL
Sean Quinlan | Dean, CLASS | sent - judge |  | FALSE
Dennis Becker | Dean, CNR | sent - judge |  | FALSE
Ginger Carney | Dean, COS | sent - judge |  | TRUE
Ben Hunter | Dean, Libraries | sent - judge |  | FALSE
Brian Tibayan | Post Doc Fellow, EHHS | sent - judge |  | TRUE
Rob Caisley | Chair, Theatre Arts | sent - judge | GRAD FAC | FALSE
Michael Brandt | Faculty, Theatre Arts | sent - judge |  | TRUE
Casey Doyle | Chair, Art & Design | sent - judge |  | FALSE
Ann Frost | Assoc Dean Grad Studies, EHHS | sent - judge | GRAD FAC | TRUE
Laura Holyoke | Chair, Leadership & Counceling, EHHS |  |  | FALSE
Dev Shrestha | Chair, Chem/Bio Engr | sent - judge | GRAD FAC | FALSE
Steve Wang | Chair, Comp Sci |  |  | FALSE
Margaret Pinnell | Director, CETL | sent - judge |  | TRUE
Diane Carter | Director, COMM1101 | sent - judge |  | FALSE
Alexandra Teague | Chair, English |  |  | FALSE
Jennifer Ladino | Director MA English | sent - judge | GRAD FAC | FALSE
Diane Baumann | Faculty, Anthropology |  |  | FALSE
Katharine E. Kolpan | Faculty, Antrhopology | sent - judge | GRAD FAC | FALSE
Romuald Afatchao | Assoc Dir, Martin Inst. | sent - judge |  | FALSE
Tanya Miura | Chair, Biological Schi |  |  | FALSE
Timothy Johnson | Chair, Maths |  |  | FALSE
Don Edgar | Chair, Ag Ed, Leadership. & comm |  |  | FALSE
Benton Glaze | Chair, Ani Vet & Food Sci |  |  | FALSE
Shiyi Chen | Faculty, FCS |  |  | FALSE
Michelle (Shelley) McGuire | Director, FCS | sent - judge |  | FALSE
Joseph Kuhl | Interim Chair, Plant Sci |  |  | FALSE
Kamal Khadka | Faculty, Plant Sci |  |  | FALSE
Frank Wilhelm | Chair, Fish & Wildlife | sent - judge |  | FALSE
Kattlyn Wolf | Ag Ed | sent - judge | GRAD FAC | FALSE
Ginny Lane | FCS, Nutritional Sci | sent - judge | GRAD FAC | TRUE
Allan Caplan | Plant Sci |  | GRAD FAC | FALSE
Hasan Jamil | Comp Sci |  | GRAD FAC | FALSE
Jaap Vos | Env Sci |  | GRAD FAC | FALSE
Thomas Williams | Earth & Spatial Sci |  | GRAD FAC | FALSE
FALSE